## Sheet1
Timeline (This template assumes a full-day in-person educational event in mid-October) | Other
June/July | Suggested Planning Committee Roles: | Potential Partner Orgs:
Finalize event date, location, and goals | Marketing | local universities
Draft event budget | Registration | local municipal league | (example)
Form planning committee | Venue Logistics | local council of governments | (example)
Identify and research potential speakers | Caterer Logistics | state association of counties | (example)
Book the venue | Speaker Management | BAP
Begin outreach to speakers and confirm availability | Agenda / Run of Show planner | ELGL
Create draft event schedule |  | FEI
Build event registration page | Canva templates from Atlanta chapter | GFOA
Design branding and create social media calendar | Social Media | ICMA
Start conversations with partner orgs - how would they like to be involved? Sponsor a coffee break, provide a speaker, booth, etc. | Homepage | IIA
IMA
| Suggested social posts/emails: | NABA
| Save the Date | NAPA
August | 1st Speaker Announcement | NARC
Launch registration | 2nd Speaker Announcement | NASACT
First email marketing send "Save the Date" | 3rd Speaker Announcement
First social media post "Save the Date" | Full agenda released
Secure speakers and collect bios/headshots, consider asking speakers for a 15-30 second video intro (commercial) to post on socials | Early bird reg ends on (date)
1 more week for early bird reg
2 more days for early bird reg
Book A/V vendor if needed | (email only) last day for early bird reg
Contact caterer(s) for quotes | Speaker videos
Order event swag | "We saved a seat for you"
Monitor registration updates | 10 days til we're together
Design volunteer roles/responsibilities | Can't wait to see you
Continue weekly social posts | Sold out - we'll see you next time!
(social only) day-of photo with quote from speaker
September | (social only) day-of video, 15-20 seconds
Finalize catering contract, menu, estimated headcount
Finalize event schedule
Schedule speaker teaser posts
Create blog or video content
Collect dietary preferences
Plan day-of logistics and volunteer needs
Order printed materials
Send reminder emails
Early Bird event registration ends
Confirm swag delivery
Determine method for CPE collection
Recruit volunteers
Begin planning next event, to advertise at this event
October
Confirm final headcount with caterer
Assemble event kits
Hold speaker briefing
Post social media countdowns and FAQs
Print attendee lists and sign-in sheets
Conduct venue walkthrough and A/V test
Prepare volunteer briefing docs
Send final logistics email to attendees
Compile run of show, assign emcee duties
Begin compiling "house slides" - on screen between sessions
Event Day
Arrive early for setup
Have printed/digital run-of-show
Ensure check-in process runs smoothly
Trial run A/V
Manage volunteers
Offer registration for your next event
2-3 social media posts throughout day
Track CPE information
Distribute post-event survey
Day After
Send thank-you emails to speakers, partners, sponsors, etc
Share photos and highlights on social media
Later
Debrief and document lessons learned
Review survey results
Distribute participants' CPEs